## Slide 1
Austin Elementary
Replacement School Update
March 18, 2015

## Slide 2
Austin ES Replacement School Update
Agenda
Timeline Update
Feasibility Study: Renovate & Building Addition
vs. Replacement School

## Slide 3
Austin ES Replacement School Modified Timeline
Identify Swing Space Ongoing
Solicit Design Professional Mar- June 2015
**(New) Feasibility Study Mar – April 2015
Planning / Design June 2015 – April 2016
Decommission and Vacate Austin ES May 2016
(Last day of classes)
Move to Swing Space Location May 2016 – June 2016
(August 2016 School Year Start)
Demolition and Rebuild of Austin Sept 2016 – June 2018
FFE & Equipment for Austin ES July 2018
Occupy New Austin ES August 2018
Note: Dates subject to change and fluctuation de to new Feasibility Study
Potential project schedule re-set depending upon outcomes

## Slide 4
Austin ES Feasibility Study
Addition & Renovation vs. New Replacement Building
Purpose:
Survey the entire existing facilities and sites to determine the best use of existing space in conjunction with any necessary facility addition or renovation to meet the educational and programmatic needs of Austin ES based on the current projections for the next five years (through 2021).
This includes evaluating the facility needs [i.e. MEP systems, ADA provisions, Fire Life Safety (above and below ceilings) etc.] to be in compliance with DCSD, the Department of Education (DOE), and all federal, state, and local code requirements. Also include a space assessment for classrooms for the future while eliminating existing portable classrooms on site with one contiguous building ig addition.

## Slide 5
Austin ES Feasibility Study
Addition & Renovation vs. New Replacement Building
Deliverable based upon future student enrollment:
Recommendation of the core student capacities (i.e. gym, cafeteria, & media center)
Building plan for renovation work
Determination of the most suitable location for a possible facility expansion and site plan for this future addition
Renovation and addition cost model
Austin Elementary Projected Enrollment
Year Enrollment
2011 653
2012 647
2013 630
2014 637
2015 642
2016 655
2017 671
2018 678
2019 686
2020 691
698
as of 3-2015 provided by DCSD Planning Dept

## Slide 6
Thank You